## Slide 1
EEA FM 2014-2021
ANNUAL MEETING 2020
Special Service EEA FM - National Focal Point
General Secretariat for Public Investments & NSRF
Status of Programmes - Greek managed programmes

## Slide 2
* On the condition of further elaboration of PDP 1
Programmes | Budget | Modalities | Programme Agreement | Ministerial Decree - PIA | Status of Implementation
B - Roma Inclusion and Empowerment | 7 ME (5ME + 2ME) | 2 predefined projects, 3 small grant schemes and bilateral activities | 10/7/2020 | 21/9/2020 | Preparation and national funding lines for supporting infrastructure Imminent invitations(calls) to PPs Preparations of public procurement and implementation procedures
D - Water Management | 5 ME (4ME + 1ME) | 2 open calls, 1 small grant scheme and bilateral activities | 26/11/2019 | 21/3/2020 | Call 1.1 Imminent for publication Call 1.2 Published-Deadline 11/2/2021
E - Renewable Energy, Energy Efficiency | 10 ME (7,5ME + 2,5ME ) | 1 open call, and bilateral activities | 6/6/2019 | 21/3/2020 | Call Published-Deadline 23/11/2020 Overwhelming response-Quality proposals
F - Good Governance, Accountable Institutions, Transparency | 8,2ME (7ME + 1,2ME) | 3 predefined projects and bilateral activities | 25/9/2020 | Imminent | Imminent MD-PIA in Off. Gazz. Preparation towards Project contracts Preparation of Project partnership agreements
G -Asylum and Migration (Capacity building of national asylum and migration management systems) | 19,4 ME (16,5ME + 2,9 ME) | 7 predefined projects, 1 small grant scheme and bilateral activities | 26/11/2019 | 21/4/2020 | Imminent submission of 3 project proposals PA amendment for 3 projects 1 project with pending term for shelter building availability
Status of Greek managed Programmes

## Slide 3
B-Roma inclusion and empowerment
Annual Meeting, 26 November 2020
Programme Operator:
Special Service “Executive NSRF Structure
Division of Employment and Social Economy”
General Secretariat for Employment
Ministry of Labour & Social Affairs

## Slide 4
B-Roma inclusion and empowerment Developments and current status
Visit to Katerini, technical meeting with the local authorities and on the spot visit to the Roma camp, February 2020
Technical meeting at the PO’s premises, finalization of Supplementary Information, February 2020
Signature of the Programme Agreement, July 2020
Meeting between the Deputy Minister of Labour and Social Affairs, the Deputy Minister of Development and Investments, the General Secretary for Social Solidarity & Fight against Poverty, the PO and Roma representatives, July 2020
Rules of Procedures of the Cooperation Committee Document adopted, August 2020
Ministerial Decree – PIA published in Official Gazette and in effect, September 2020
Website in operation
Invitation – Call to PDP 1 Project Promoter, October 2020
3rd Annual Meeting, 26 November 2020

## Slide 5
3rd Annual Meeting, 26 November 2020
B-Roma inclusion and empowerment Developments and current status PDP 2
National funding lines from the Public Investments Programme for the supporting infrastructure of PDP 2/Katerini settlement have been registered, October 2020
The Municipality of Katerini has updated the list of families-beneficiaries of the PDP2 and has taken actions to facilitate the smooth integration with the local urban network
  Indicatively:
  All school age children (56 in the primary school & 8 in the high school) go to school every day, with no absences
  Public bus line reaches the camp area and connects it with the town. It is the bus line used by the Roma students for their daily transport to school
  Trash and recycling bins have been placed in the area
To prevent the spread of the COVID-19 in the Roma Settlement the Municipality catered for:
  Disinfection services
  Door-to door Information and Sanitary Advice Campaign
  Provision of food and bottled water

## Slide 6
3rd Annual Meeting, 26 November 2020
B-Roma inclusion and empowerment
Secretary General for Social Solidarity and Fight Against Poverty visited on the spot in Katerini and discussed with the relevant actors, including local authorities and Roma representatives

## Slide 7
3rd Annual Meeting, 26 November 2020
B-Roma inclusion and empowerment Next steps
Submission of proposal and Project contract for PDP1
Invitation/Call, submission of proposal and Project contract for PDP2
Preparation of the Call for the 3 Small Grant Schemes
Drafting and adoption of the Management and Control System at the programme level
Cooperation Committee meeting(s) by teleconference

## Slide 8
EUROPEAN ECONOMIC AREA
FINANCIAL MECHANISM
2014-2021
Hellenic Ministry of Environment and Energy
“Executive Authority of the Partnership Agreement, Environmental sector”
PROGRAMME: WATER MANAGEMENT
  ANNUAL METTING
  Thursday, November 26, 2020

## Slide 9
Signature of the Programme Agreement, November 2019
Ministerial Decree – PIA published in Official Gazette and in effect, March 2020
Management and control system at the programme level, November 2020
Call for output 1.2 “Research measures of river basin management plans” sent to FMO in July 2020 and elaborated until September 2020 - Call was published in November 2020
Call for output 1.1 “Water management systems – Desalination Units” imminent for publication
Call for output 1.3 - Small grant scheme in preparation
Bilateral initiatives: In the context of the calls, the Project Promoters (PP) are invited to submit proposals for bilateral cooperation
2 IFRs submitted
Programme webpage in operation
Covid19 pandemic affected mainly communication activities
B-Water management Developments and current status

## Slide 10
Evaluation, Selection and Project Contracts under Open calls 1.1 and 1.2
Bilateral initiatives awarded
Call for output 1.3 - Small grant scheme published
Launching and matchmaking events pending – To be further discussed
B-Water management Next steps

## Slide 11: Renewable Energy, Energy Efficiency Programme
EEA 2014-2021
3rd Annual Meeting
Tuesday 26.11.2020
GR-Energy Programme Progress
Programme Team:
Mr Markos DAMASIOTIS, Programme Manager
Dr Konstantinos PATLITZIANAS, Programme Coordinator
Mrs Maria NTIONIA, Publicity Officer
Mr Loukas Gavriil, Implementation Team
Dr Emmanouil Malliotakis, Implementation Sub team
Mrs Vasiliki Polyzoi, Project Verification of Payments Sub Team

## Slide 12
Open Call: Deadline on 23/11/2020
Key communication tool between the PO CRES and potential PPs http://eeares.cres.gr/  3 sets of Q&As have been uploaded and a total of 38 questions have been answered in detail
GRACE: All information is submitted  3 IFRs, 1APR & Open Call Information
The Audit Authority (EDEL) conducted the 1st Audit of the Programme  October 2020
Open Call for Independent Reviewer’s Registry  November 2020  Everything is ready for the evaluation process.
E-Energy Developments and current status

## Slide 13
Collection of Applications of Project Proposals & evaluation of Project Proposals by the Independent Reviewer’s Registry.
Selection of successful Project Proposals.
Submission of relevant reports and information to GRACE: 2nd APR, IFR#4, Steps 3 – 5 of Programme Call Information
E-Energy Next steps

## Slide 14: Schedule
2017
2024
June – Dec.
Jan – Dec
Jan – Dec
Jan – Dec
Jan – Dec
2022-2024
Stakeholders Meeting 01/02/2018
Official Submission of Concept Note 17/07/2018
Sign of MoU
31/10/2017
Signing of Programme Agreement 26/6/2019
Preparation of the Open Call.
2nd Semester of 2019
2017
2018
2019
2020
2021
2022-2024
Completion date
Implementation of Programme Phase
2021 - 2024
Completion of tender documents
February 2020
Launch: 22/07/2020
Deadline: 23/11/2020
Proposal’s Evaluation
Start Date: Jan2021

## Slide 15
EUROPEAN ECONOMIC AREA
FINANCIAL MECHANISM
2014-2021
PROGRAMME F
Good Governance, Accountable Institutions and Transparency
  Programme Operator
  Hellenic Ministry of Digital Govergence
  ANNUAL METTING
  Thursday, November 26, 2020

## Slide 16
MoU amendment in March 2020:
  New Programme Operator designated: Management & Implementation Authority for Information Communication Technologies (M&IA ICT)
  New Project Promoters:
  PDP1: Ministry of Digital Governance/General Secretariat of Digital Governance & Simplification of Procedures
  PDP2: National Authority of Transparency
Programme Agreement signed on 25/9/2020 – MD PIA immminent
The Programme Operator:
  coordinated procedure of supplementary information at the national level
  coordinated and supported the maturity of the project partnership agreements
  organized virtual meeting on 23.10.2020 (35 people) with the participation of PPs -Partners, OECD, NFP and FMO to kick start the implementation
  participated to training on the MCS at the national level, organized by the NFP & MOU
  gathered the needs expressed by Project Promoters and prepares implementation Management Costs activities
  commented on the draft MD – PIA
  initiated collaboration with Donors & FMO for the bilateral initiatives’ partners’ matchmaking
  prepares for implementation according to MCS
The Project Promoters:
  participated to training on the MCS at the national level, organized by the NFP & MOU
  matured and elaborated project partnership agreements
  get the internal implementation team together
  expressed their needs for support through management cost activities
  participated to PO’s coordinated action with Donors for matchmaking with potential bilateral partners/initiatives
3rd Annual Meeting, 26 November 2020
F-Good Governance, Accountable Institutions and Transparency
Developments and current status

## Slide 17
Setup of Coordination Committee and call for 1st meeting.
Issue of calls to Project Promoters and PO relevant Unit to support Programme implementation
Liaise with the Special Service of the Integrated System to verify smooth operation of the System
Submission of Predefined Projects by Project Promoters with a reviewed timeline + necessary documents
Appraisal of Predefined Projects & signing of project contracts (criteria of assessment, decision on conditions)
Assist Project Promoters to finalise their partnership agreements where needed
Continue supporting building the pipeline of bilateral activities
Draft the Communication Plan and take first comm actions with the support of experts
Coordinate actions to update the baseline values for some indicators
Inform the NFP on how and when Programme conditions are met
Assess the impact of the pandemic on project implementation and bilateral ambitions
Monitor risk and take appropriate actions
Next steps and medium-term actions
  Capacity building of Project Promoters in a timely manner -> technical support provision and organization of focused learning activities
  Framing bilateral activities and sizing support needed -> coordinate stakeholders where needed
  Impact of uncertaintity of pandemic to programme and project activities in relation to end of eligibility period -> well documented and realistic review of PDP timelines
  Timely conclusion of partnership agreements -> provide expertise through targeted technical support
  Unforeseen circumstances or changes with high impact in the environment of the programme / projects and the stakeholders in general  escalation of risk mitigation options to level consequences
Challenges and indicative proactive actions
3rd Annual Meeting, 26 November 2020
F-Good Governance, Accountable Institutions and Transparency
Next steps

## Slide 18
EUROPEAN ECONOMIC AREA
FINANCIAL MECHANISM
2014-2021
Programme G
Capacity Building of National Asylum and Migration Management Systems
Programme Operator
  European and Development Programmes Division
  Hellenic Ministry of Citizen Protection
  ANNUAL METTING
  Thursday, November 26, 2020

## Slide 19
3rd Annual Meeting, 26 November 2020
G - Capacity Building of National Asylum and Migration Management Systems

## Slide 20
3rd Annual Meeting, 26 November 2020
G - Capacity Building of National Asylum and Migration Management Systems
Developments and current status
Invitation/Call for Proposals
•Available Budget: € 15.487.750*
•Number of Pre-Defined Projects included: 6
•Project Promoters addressed:
pdp1 Appeals Authority: Preparation of Donor project partnership agreement – Submission in December 20
pdp2 Asylum Service: Preparation of Donor project partnership agreement – Submission in December 20
pdp3 Min of Migration (GD Fin&Admin): Preparation of Donor project partnership agreement – Submission in December 20
pdp5 Greek Ombudsman: Fin management resolved – Pending issue with content (FRA-MinMig MoU) (PA amend?)
pdp6 Hellenic Police: Request of project partner for the scientific expertise (PA amend?)
pdp7 Reception and Identification Service: Pending Shelter building availability (PA conditionality)
*PDP 4, the Small Grant Scheme and the Managements Costs will be included in separate Calls

## Slide 21
3rd Annual Meeting, 26 November 2020
G - Capacity Building of National Asylum and Migration Management Systems
Next steps
Programme Agreement Amendment – Proposal to be submitted
Amendments under consideration:
PDP 1&2 Withdrawal of conditions for verification as entities not under same ministry anymore
PDP 4 EKKA Unaccompanied minors: Split to 2 projects (PDP4+PDP8) according to new sectorial setup & competences
PDP 5 Greek Ombudsman-FRA: Possible issues related to MinMig MoU
PDP 6 Hellenic Police: New project partner for the scientific expertise

## Slide 22
3rd Annual Meeting, 26 November 2020
G - Capacity Building of National Asylum and Migration Management Systems
Next steps
Implementation Level
Project Contracts for 3 PDPs up to February 2020 (PDP 1,2,3)
Call and selection for Management cost activities to support PPs
Programme Agreement Amendment
Proposal to be submitted - Amendments under consideration:
PDP 1&2 Withdrawal of conditions for verification as entities not under same ministry anymore
PDP 4 EKKA Unaccompanied minors: Split to 2 projects (PDP4+PDP8) according to new sectorial setup & competences
PDP 5 Greek Ombudsman-FRA: Possible issues related to MinMig MoU
PDP 6 Hellenic Police: New project partner for the scientific expertise